## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the milestone description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use the progress column to add how much of the project you finished by adding a percentage number • Add the day you started your project in the start date column • Finish your calculations by filling in the number of days you need to complete your project in the days column

## Dark
PROJECT: 600-12 Volt LLC DC-DC Converter
Team: sdmay26-45 |  |  |  |  | Legend: | On track |  |  |  |  | High Risk |  |  |  |  | Med Risk |  |  |  |  | Low Risk
Creator: Caleb Rezmer
Project start date: | 2025-08-31 |  |  |  |  | August | [6 empty] | September | [27 empty] | October | [36 empty] | November
Scrolling increment: | 0 | time axis 2025-08-31 to 2025-12-16
Task description | Category | Assigned to | Progress | Start | Days | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T
Initial Faculty Mentor Meeting | Milestone |  |  | 2025-09-17 | 1 | bar: W
Research and Learn About LLC Converters | On Track | Everyone | 100% | 2025-09-01 | 20
Find viable models to use for reference | Low Risk | Everyone | 100% | 2025-09-14 | 14
Decide on a model to use for converter topology | Milestone | Everyone | 100% | 2025-09-27 | 1 | bar: S
Build a working converter simulation | Med Risk | Caleb | 100% | 2025-09-28 | 24
Build a working precharge simulation | Low Risk | Hunter | 100% | 2025-09-28 | 24
Simulations Complete | Goal | Everyone for respective subcircuits | 75% | 2025-10-21 | 1 | T: 2
Design Validation (Technical Analysis Document) | Goal | Everyone for respective subcircuit | 60% | 2025-10-21 | 1 | T: 2
New Rectifier and Output Filtering Specified | Med Risk | Caleb and Chandler | 100% | 2025-10-05 | 17
Chosen Parts Sourced From Digikey and Mouser | On Track | Diego | 100% | 2025-09-27 | 14
Altium Schematic Design | Med Risk | Everyone for respective circuit | 20% | 2025-09-28 | 34
Altium Schematic Complete | Goal | Everyone for respective circuit | 0% | 2025-10-31 | 1 | F: 2
Faculty Mentor Progress Meeting 2 | Milestone |  | 100% | 2025-10-22 | 1 | bar: W
SLA Printing For Bobbin | High Risk | Bixler | 80% | 2025-10-21 | 10
Transformer Parts Ordered | Goal | Hunter and Caleb | 100% | 2025-10-31 | 1 | F: 2
Transformer Build Process and Test Plan | On Track | Bixler and Hunter | 100% | 2025-10-25 | 14
Transformer LCR Measurements | On Track | Bixler and Hunter | 0% | 2025-11-09 | 21
Transformer Isolation Test | On Track | Bixler and Hunter | 0% | 2025-11-09 | 21
KiCAD PCB Layout Process (Ahead) | On Track | Caleb and Chandler | 100% | 2025-11-01 | 30
Layout Complete | Milestone | Caleb and Chandler | 100% | 2025-10-31 | 1 | bar: F
PCB Ordered | Goal | Caleb (JLC PCB) | 100% | 2025-11-05 | 1 | W: 2
PCB Test Plan | On Track | Chandler, Diego, Wesley, and Caleb | 90% | 2025-10-31 | 14
Task 6
Task 7
Task 8
Task 9
Task 10
Task 11
Task 12
Task 13
Task 14
Task 15
Task 16
Task 17
Task 18
Task 19
Task 20
Task 21
Task 22
Task 23
Task 24
Task 25
Task 26
Task 27
Task 28
Task 29
Task 30
Task 31
Task 32
Task 33